## RT-Index
RT-ID | Subject | BG | BR | SCR | API | DB | TEST | EVID | RC | IMP | EVAL
RT-001 | CI Log Intake | BG-001 | BR-001 | SCR-001 | API-001, API-002 | DB-001, DB-002 | TEST-001..004 | EVID-001 | RC-001, RC-014 | IMP-016 | —
RT-002 | Repo Linking | BG-001 | BR-002 | SCR-002 | API-003 | DB-003, DB-004 | TEST-005..007 | EVID-002 | RC-002, RC-019 | IMP-015 | —
RT-003 | Root-Cause Analysis | BG-001, BG-005 | BR-003, BR-012 | SCR-003 | API-004 | DB-005, DB-006 | TEST-008..010 | EVID-003 | RC-003, RC-009 | IMP-009 | EVAL-001
RT-004 | Repair Plan | BG-002, BG-005 | BR-004, BR-012 | SCR-004 | API-005 | DB-007 | TEST-011..013 | EVID-004 | RC-004 | IMP-023 | EVAL-002
RT-005 | Approval Workflow | BG-004 | BR-005 | SCR-005 | API-006, API-007 | DB-008 | TEST-014..017 | EVID-005 | RC-005, RC-010 | IMP-019 | —
RT-006 | Evidence Export | BG-004 | BR-006, BR-011 | SCR-006 | API-008 | DB-009, DB-010 | TEST-018..020 | EVID-006 | RC-006, RC-011 | IMP-025 | —
RT-007 | Analytics | BG-006 | BR-007 | SCR-007 | API-009 | DB-011, DB-012 | TEST-021..022 | EVID-007 | RC-007 | IMP-024 | —
RT-008 | Secret Masking | BG-004, BG-005 | BR-008 | (cross) | (cross) | DB-013 | TEST-023..024 | EVID-008 | RC-008, RC-014, RC-019 | IMP-016 | —
RT-009 | PromptOps Governance | BG-005 | BR-009 | (admin) | API-010 | DB-014, DB-015 | TEST-025 | EVID-009 | RC-012, RC-020 | IMP-009, IMP-023 | EVAL-001/002
RT-010 | Flaky Detection | BG-003 | BR-010 | SCR-003 sub | API-004 ext | DB-016 | TEST-026 | EVID-010 | RC-013 | IMP-015 | —
RT-011 | Audit Schema | BG-004 | BR-011 | (export) | API-008 | DB-010 | TEST-027 | EVID-011 | RC-015 | IMP-025 | —
RT-012 | Eval Gate Enforcement | BG-005 | BR-012 | (CI internal) | (internal) | DB-017, DB-018 | TEST-028 | EVID-012 | RC-016 | IMP-022 | EVAL-001/002
RT-013 | Multi-Tenant Isolation | BG-004 | (NFR) | all | all | tenant_id RLS | TEST-013-A | EVID-013 | RC-006, RC-021 | IMP-020 | —
RT-014 | Role/Permission Model | BG-004, BG-005 | (NFR) | SCR-005 admin | API-006 | DB-008 + role_perms | TEST-014-A | EVID-014 | RC-022 | IMP-024 | —
RT-015 | Idempotency & Replay | BG-001 | BR-001 | SCR-001 | API-001 | idempotency_keys | TEST-001-A | (rolls EVID-001) | RC-023 | — | —
RT-016 | Cost Ceiling Enforcement | BG-006 | (NFR) | SCR-007 admin | API-009 | tenant_quotas | TEST-021-A | — | RC-024 | IMP-017 | —
RT-017 | Drift Detection | BG-005 | BR-012 | (admin) | (internal) | drift_events | TEST-028-A | — | RC-020 | IMP-009 | EVAL-001/002
RT-018 | Customer Success / QBR | BG-006 | (commercial) | SCR-007 exec | API-009 | qbr_packs | — | EVID-007 ext | RC-025 | IMP-024 | —
RT-019 | Data Residency Config | (NFR) | (compliance) | (admin) | API-010 | tenant_region | TEST-013-B | — | RC-026 | IMP-021 | —
RT-020 | Replay/Regression Harness | BG-005 | BR-012 | (internal) | (internal) | regression_runs | TEST-028-B | — | RC-027 | IMP-014, IMP-025 | EVAL-001/002

## BR-Mapping
BR | Title | Rep US | SCR | API | Acceptance anchor | Edge case | Negative path | Exit gate
BR-001 | CI Log Intake | US-001 | SCR-001 | API-001, API-002 | Webhook 5s p95 | Matrix run, multi-job | Unsigned webhook → 401 | TEST-001..004
BR-002 | Repository Linking | US-008 | SCR-002 | API-003 | OAuth issues install token | Archived repo, SSO required | Invalid PAT → 403 + rotate | TEST-005..007
BR-003 | Root Cause Analysis | US-005, US-006 | SCR-003 | API-004 | Inference p95 ≤ 8s | Mixed-cause, non-English | Model timeout → rules fallback | EVAL-001 ≥ 85% MVP
BR-004 | Repair Plan Generation | US-005 | SCR-004 | API-005 | JSON schema valid | Protected branch | Generation fails → manual form | EVAL-002 ≥ 80% MVP
BR-005 | Approval Workflow | US-003, US-007 | SCR-005 | API-006, API-007 | Signature + justification ≥ 20ch | OOO delegation | Rejected → optional re-plan max 3 | 100% executed plans signed
BR-006 | Evidence Export | US-004, US-010 | SCR-006 | API-008 | ZIP HMAC-signed; receipt 10y | >100MB split-archive | Signing key down → block, page | EVID verifiable offline
BR-007 | Analytics Dashboard | US-002 | SCR-007 | API-009 | Dashboard p95 ≤ 2s | Sparse tenant | — | TEST-021..022
BR-008 | Deterministic Masking | US-008 | (cross) | n/a | 0 leak N=500 | Provider-specific tokens | Mask fail → block, no fallback | TEST-023..024
BR-009 | PromptOps Governance | US-009 | (admin) | API-010 | Promotion blocked on red EVAL | Rollback ≤ 30s | Red EVAL promotion → 409 | PromptOps L3
BR-010 | Flaky Detection | (Platform) | SCR-003 sub | API-004 ext | Flaky list ≤ 15min stale | Parameterized tests | FP > 5% → tune | ±10% parity vs BuildPulse
BR-011 | Audit Schema | US-010 | (export) | API-008 | Schema versioned, JSON Schema 2020-12 | — | Consumer breakage → deprecation | TEST-027
BR-012 | Eval Gates | US-009 | (CI) | (internal) | EVAL gates enforced in CI | Drift PSI > 0.2 → alert | Eval-set corruption → block all promotions | TEST-028

## TestCoverage
TEST-ID | Type | Subject | Owner | Automation | Frequency | Exit Gate
TEST-001 | Integration | Intake webhook happy path | BE | CI | every PR | 5s p95
TEST-001-A | Integration | Intake idempotency replay | BE | CI | every PR | 0 duplicates
TEST-002 | Integration | Intake schema validation | BE | CI | every PR | 422 on invalid
TEST-003 | Negative | Unsigned webhook | Sec | CI | every PR | 401
TEST-004 | Negative | Oversized payload | BE | CI | every PR | 413
TEST-005 | Integration | OAuth happy path | BE | Manual MVP, CI P4 | weekly | install token issued
TEST-006 | Negative | Revoked PAT | BE | CI | every PR | 403 + rotate hint
TEST-007 | Integration | Repo verify | BE | CI | every PR | SHA ≤ 10s
TEST-008 | AI eval | EVAL-001 gold-set run | AI | CI | every prompt PR | ≥85% MVP
TEST-009 | Negative | RCA model timeout | AI | CI | every PR | fallback fires
TEST-010 | Integration | RCA writes prompt_run | BE | CI | every PR | row with pins
TEST-011 | AI eval | EVAL-002 gold-set run | AI | CI | every prompt PR | ≥80% MVP
TEST-012 | Schema | Plan JSON schema | BE | CI | every PR | 100% validity
TEST-013 | Negative | Plan touches protected branch | BE | CI | every PR | dual-approver flagged
TEST-013-A | Security | Multi-tenant RLS pen-test | Sec | Manual quarterly | quarterly | 0 crossover
TEST-013-B | Compliance | EU residency config | SRE | CI | every PR | data resident eu-west
TEST-014 | Integration | Approval sign happy path | BE | CI | every PR | append-only
TEST-014-A | RBAC | Permission matrix sweep | Sec | CI | every PR | all rows pass
TEST-015 | Negative | Approval token expired | BE | CI | every PR | 410
TEST-016 | Integration | Dual-approval prod path | BE | CI | every PR | both signatures
TEST-017 | UX | Slack DM deep-link | FE | Manual | weekly | opens SCR-005
TEST-018 | Integration | Evidence ZIP generate | BE | CI | every PR | manifest valid
TEST-019 | Security | Evidence HMAC verify | Sec | CI | every PR | offline-valid
TEST-020 | Compliance | 10-year retention | SRE | CI | every PR | object-lock
TEST-021 | Performance | Dashboard p95 load | FE | CI | every PR | ≤2s
TEST-021-A | FinOps | Cost ceiling throttle | BE | CI | every PR | throttle at 100%
TEST-022 | Integration | CSV export schema | BE | CI | every PR | columns stable
TEST-023 | Security | Mask v1 red-team | Sec | CI | every PR | 0 leaks N=500
TEST-024 | Negative | Mask engine failure | Sec | CI | every PR | block, no fallback
TEST-025 | Governance | Prompt promotion blocked when EVAL red | AI | CI | every PR | 409
TEST-026 | Parity | Flaky vs BuildPulse | AI | Manual quarterly | quarterly | ±10% overlap
TEST-027 | Schema | audit_export schema | BE | CI | every PR | JSON Schema 2020-12 valid
TEST-028 | AI eval | Eval gate enforcement | AI | CI | every PR | gate fires
TEST-028-A | Drift | PSI > 0.2 alert | AI | CI | every PR | alert generated
TEST-028-B | Regression | Replay harness | AI | CI | every PR | parity ≥ 95%

## EvalCards
Attribute | EVAL-001 (RCA) | EVAL-002 (Repair Plan)
Task | 12-class classification of CI failure | Structured repair plan; useful = approver accepts with ≤1 minor edit
Primary metric | Slice-weighted macro-F1 | Usefulness rate
Secondary | Top-3 accuracy, confidence calibration (ECE), p95 latency, refusal rate | Schema validity 100%, hallucinated-file rate 0 (hard gates)
Gold-set size | N=250 stratified | N=250 incidents with approved-plan ground truth
Label provenance | 2-of-2 IAA + 3rd-annotator tiebreak | Approved-plan ground truth or expert-authored
Slice definitions | Class, provider, language, log-length quartile, repo-age quartile | Root-cause class, plan-action-type, blast-radius, language
MVP threshold | 85% | 80%
Pilot threshold | 90% | 85%
Promotion target | 92% | 88%
Fairness floor | No provider/language slice < 80% | Usefulness parity across action-type slices within 8pp
Drift detection | PSI > 0.2 alert; chi-square on output | Schema validity trend; rejection-reason clustering
Retraining trigger | >3pp drop any slice 7-day OR PSI > 0.2 sustained 48h | Usefulness < threshold for any slice 7-day OR any hallucinated-file event
Refresh cadence | Quarterly | Quarterly
Label-quality audit | Monthly 5% blind re-label, κ ≥ 0.75 | Monthly, κ ≥ 0.70 (subjective task tolerates lower)
Owner | AI Lead | AI Lead
Escalation | AI Lead → VPE → CTO | AI Lead → VPE → CTO

## RC-Linkage
RC | Comment | Severity | Linked RT/BR | Target Date | Status
RC-001 | Intake XML schema validation before persist | Medium | RT-001 / BR-001 | Phase 1 end | Closed
RC-002 | OAuth scope read-only minimal | High | RT-002 / BR-002 | Phase 1 end | Closed
RC-003 | RCA card must show why not just what | High | RT-003 / BR-003 | Phase 2 end | Closed
RC-004 | Repair plan explicit blast-radius field | High | RT-004 / BR-004 | Phase 2 end | Closed
RC-005 | Approval justification min 20 chars | Medium | RT-005 / BR-005 | Phase 2 mid | Closed
RC-006 | Multi-tenant pen-test | Critical | RT-013 | Phase 4 mid | Open
RC-007 | Analytics drill-through to incident | Medium | RT-007 / BR-007 | Phase 3 end | Closed
RC-008 | Mask false-positive rate measured | High | RT-008 / BR-008 | Phase 2 mid | Open
RC-009 | RCA confidence calibration (ECE) reported | High | RT-003 | Phase 2 end | Open
RC-010 | Approval delegation when OOO | Medium | RT-005 | Phase 4 mid | Open
RC-011 | Evidence pack split-archive for >100MB | Medium | RT-006 / BR-006 | Phase 2 end | Closed
RC-012 | Prompt diff visible before promotion | High | RT-009 / BR-009 | Phase 2 end | Closed
RC-013 | Flaky parity vs BuildPulse | Medium | RT-010 / BR-010 | Phase 3 end | Open
RC-014 | Secret-pattern provider extension | High | RT-001, RT-008 | Phase 2 mid | Open
RC-015 | Audit-export schema deprecation policy | Medium | RT-011 / BR-011 | Phase 3 end | Closed
RC-016 | Eval gate must be CI-blocking | Critical | RT-012 / BR-012 | Phase 2 end | Closed
RC-017 | Demo deterministic seed | Medium | (cross) | Phase 3 end | Open
RC-018 | Cross-persona reading order | Low | (doc-level) | Phase 3 mid | Closed
RC-019 | Mask policy version pinned in every prompt_run | High | RT-008 | Phase 2 mid | Closed
RC-020 | Drift detector emits alert at PSI > 0.2 | High | RT-003, RT-017 | Phase 2 end | Open
RC-021 | RLS on tenant_id enforced at query layer | Critical | RT-013 | Phase 1 end | Open
RC-022 | RBAC matrix documented and tested | High | RT-014 | Phase 2 end | Open
RC-023 | Idempotency-Key REQUIRED on writes | High | RT-015 | Phase 1 end | Closed
RC-024 | Cost ceiling soft (80%) + hard (100%) alerts | High | RT-016 | Phase 2 end | Open
RC-025 | QBR template for CSM with KPI rollups | Medium | RT-018 | Phase 4 mid | Open
RC-026 | Data-residency admin flag per tenant | High | RT-019 | Phase 4 mid | Open
RC-027 | Replay/regression harness | Medium | RT-020 | Phase 3 end | Open
RC-028 | Model fallback registry with auto-failover | High | RT-004, RT-009 | Phase 2 end | Open
RC-029 | Chaos test pack | Medium | (cross) | Phase 4 mid | Open
RC-030 | Security-approver role for secret-rotation plans | High | RT-005 | Phase 4 mid | Open
SUMMARY
Total | 30
Open | 17
Closed | 13

## IMP-Linkage
IMP | Title | Phase | Effort (hrs) | RT links | Status
IMP-001 | Mask v1 patterns | 1 | 24 | RT-001, RT-008 | Critical-path
IMP-002 | OAuth app submission | 1 | 8 | RT-002 | Phase 1
IMP-003 | Idempotency-Key middleware | 1 | 12 | RT-015 | Critical-path
IMP-004 | Approval signature scheme | 2 | 20 | RT-005 | Critical-path
IMP-005 | Evidence ZIP signer | 2 | 32 | RT-006 | Critical-path
IMP-006 | Prompt registry mirror | 2 | 24 | RT-009 | Phase 2
IMP-007 | EVAL gate CI integration | 2 | 16 | RT-012 | Critical-path
IMP-008 | Analytics rollup batch | 3 | 16 | RT-007 | Phase 3
IMP-009 | Drift detector PSI | 2 | 28 | RT-003, RT-017 | Phase 2
IMP-010 | RBAC matrix | 2 | 20 | RT-014 | Phase 2
IMP-011 | Slack/email integration | 2 | 16 | RT-005 | Phase 2
IMP-012 | CSV export | 3 | 8 | RT-007 | Phase 3
IMP-013 | Approver feedback loop | 3 | 16 | RT-005, RT-003 | Phase 3
IMP-014 | Replay/regression harness | 3 | 32 | RT-020 | Phase 3
IMP-015 | Chaos test pack | 4 | 40 | RT-010, RT-013 | Phase 4
IMP-016 | Secret-scanning provider extension | 2 | 24 | RT-008 | Phase 2
IMP-017 | FinOps cost ceiling | 2 | 20 | RT-016 | Phase 2
IMP-018 | Demo dry-run + det seed | 3 | 16 | (cross) | Critical-path
IMP-019 | On-call rotation pack | 4 | 24 | RT-005 | Phase 4
IMP-020 | Risk owner staffing + RLS hardening | 4 | 16 | RT-013 | Phase 4
IMP-021 | EU data residency | 4 | 80 | RT-019 | Phase 4
IMP-022 | Gold-set governance + label audit | 2-cont | 12 | RT-012 | Recurring monthly
IMP-023 | Model fallback registry | 2 | 24 | RT-003, RT-004 | Phase 2
IMP-024 | CS playbook + QBR template | 4 | 24 | RT-018 | Phase 4
IMP-025 | Audit-export schema deprecation policy | 3 | 12 | RT-011 | Phase 3
TOTAL HOURS |  |  | 564

## RiskRegister
R-ID | Risk | L | I | Score | Owner | Phase | Mitigation | Residual
R-01 | EVAL-001 fails to reach 90% on pilot data | 3 | 5 | 15 | AI Lead | 2-3 | IMP-022, rules fallback, slice analysis | 10
R-02 | Secret leaks through Mask v1 gap | 2 | 5 | 10 | Sec Lead | 1 | Red-team N=500; deny-on-fail; IMP-016 | 5
R-03 | LLM provider outage (>4h) | 3 | 4 | 12 | AI Lead | 2 | Model fallback registry IMP-023; rules fallback | 8
R-04 | GitHub OAuth app review delays | 2 | 3 | 6 | Platform | 1 | PAT fallback in MVP | 3
R-05 | Live demo failure on judges | 2 | 5 | 10 | PM | 3 | Pre-recorded fallback IMP-018; deterministic seed | 5
R-06 | Gold-set label noise | 3 | 3 | 9 | AI Lead | 2 | IMP-022 monthly label audit | 6
R-07 | Approver burnout / fatigue | 3 | 3 | 9 | Platform Lead | 4 | Confidence auto-suppress; digest mode; IMP-019 | 6
R-08 | Multi-tenant data crossover bug | 2 | 5 | 10 | Sec Lead | 1 | RLS; per-tenant DEK; quarterly pen-test | 5
R-09 | LLM cost ceiling exceeded | 4 | 3 | 12 | Platform Lead | 2 | FinOps cost ceiling IMP-017 | 6
R-10 | EU residency demanded pre-Phase-4 | 3 | 4 | 12 | Sales | 3-4 | Roadmap pre-sell; IMP-021 acceleration | 8
R-11 | Prompt drift undetected | 3 | 4 | 12 | AI Lead | 2 | Drift detector IMP-009; canary + auto-rollback | 8
R-12 | Audit-pack schema breaks GRC tools | 2 | 4 | 8 | GRC | 3 | Versioned schema; deprecation policy IMP-025 | 4
AGGREGATE |  |  |  | 125 |  |  |  | 0